🏙️ Machi Koro

Digital Recreation — Project Work Plan

Solo Project  |  WordPress MVP → React + Python  |  2–5 Players  |  Machi Koro Plus

# Project Overview

This project is a faithful digital recreation of Machi Koro Plus for 2–5 players. The approach uses a two-stage strategy: first build a WordPress MVP with full online multiplayer support (via AJAX polling) so friends can play together from day one, then migrate to a production-quality React + Python stack with WebSocket-based real-time sync.

## Key Parameters

- Card Set: Machi Koro Plus (city-symbol cards)

- Players per table: 2–5

- Player modes: Online multiplayer in MVP (polling) → WebSocket real-time → AI opponent (phased)

- Auth: Guest play (no account) + Registered users (email sign-up, scores saved)

- Stack: WordPress MVP first, then React (frontend) + Python/FastAPI (backend)

## Technology Stack (Final)

| Layer | Technology | Purpose |
| --- | --- | --- |
| MVP Frontend | JavaScript + jQuery (WP) | Game UI, polling, player actions |
| MVP Backend | WordPress + PHP plugin | Game engine, AJAX handlers |
| MVP Database | WordPress custom DB tables | Game state, users, scores |
| MVP Realtime | AJAX polling (3–5s) | Online multiplayer sync |
| Final Frontend | React + Zustand | Production game UI |
| Final Backend | Python (FastAPI) | Game engine, REST/WS API |
| Final Database | PostgreSQL | Users, scores, game history |
| Final Realtime | WebSockets | Low-latency multiplayer sync |
| Hosting (MVP) | Any WordPress host | Shared hosting compatible |
| Hosting (Final) | Vercel + Railway/Render | Frontend + backend deploy |

# Phase 1 — Research & Design

WEEK 1–2

1.1  Game Rules Documentation

- Document every card in Machi Koro Plus with its dice activation number, effect, and cost

- Map all card interaction rules and edge cases (e.g. simultaneous activations, Blue vs Red vs Green vs Purple card order)

- Define win condition (all 4 Landmarks built)

- Clarify turn structure: Roll → Activate cards → Build phase

1.2  Game State Model

- Define data structures for: Player, Hand, Market, Landmarks, Dice, Coins, TurnState

- Map out all card effects as reusable logic functions

- Plan state transitions for each phase of a turn

1.3  UI/UX Wireframes

- Lobby / Table creation screen

- Waiting room (players joining via code)

- Main game board: player hand, shared market, opponent area, dice zone

- End game screen (scores + leaderboard)

# Phase 2 — WordPress MVP

WEEK 3–8

Goal: A fully playable online prototype where friends can join a table via code and play Machi Koro Plus together in real time (via polling). Validates game logic, lobby system, and user experience before the full stack rebuild.

2.1  WordPress Setup & Auth

- Install WordPress + chosen page builder (Elementor or similar)

- Use built-in WP user registration for email-based sign-up / login

- Guest users: session-based, no account required

- Registered users: scores saved to custom DB table after each game

2.2  Table / Lobby System

- Any user (guest or registered) can create a table

- Table creator receives a unique join code (e.g. MACHI-4829)

- Optional password protection on the table

- Other players join via code + optional password

- Waiting room shows who has joined; only the creator can press Start

- Table supports 2–5 players

2.3  Core Game Engine (PHP Plugin)

- Implement full Machi Koro Plus turn loop:

- Roll 1 or 2 dice (player choice from turn 2 onward)

- Resolve opponent Blue cards first, then own Blue/Green, then Red (opponents), then Purple (active player)

- Build phase: buy 1 establishment or 1 landmark

- Check win condition

- Card market: shared pool of Machi Koro Plus cards

- Coin economy: transactions logged per action

2.4  Online Multiplayer via AJAX Polling

- Game state stored in a custom WordPress DB table after every action

- Each player's browser polls the server every 3–5 seconds via AJAX

- Server returns latest game state; UI updates if anything changed

- Player actions (roll dice, buy card) sent instantly via AJAX POST — no waiting for the poll cycle

- Turn lock enforced server-side: only the active player's actions are accepted

- Up to 5s delay between one player's action and others seeing it — fine for a turn-based game

- No extra server software needed — works on standard shared WordPress hosting

2.5  Score System

- End-game results shown to all players in session

- Scores saved to DB only for registered users

- Basic leaderboard page for registered users (nice-to-have for MVP)

# Phase 3 — MVP Review & Migration Planning

WEEK 9–10

- Playtest the WordPress prototype with real online players

- Document all bugs, rule gaps, and UX pain points

- Note polling limitations (latency, server load) to justify WebSocket upgrade in Phase 4

- Finalize React + FastAPI architecture based on MVP learnings

- Plan database schema (PostgreSQL: users, games, scores, game_states)

- Decide on WebSocket library for real-time multiplayer (e.g. Socket.IO or native WS)

# Phase 4 — React + Python Rebuild

WEEK 11–18

4.1  Backend — Python / FastAPI

- Full game engine: all Machi Koro Plus rules implemented in Python

- REST API: create table, join table, get game state, take action

- WebSocket API: real-time game state broadcast to all players at a table

- Auth: JWT-based login, email registration, guest sessions

- PostgreSQL models: User, Table, Game, GameState, Score

4.2  Frontend — React

- Component library: Card, Market, PlayerBoard, DiceRoller, CoinCounter, LandmarkTrack

- State management: Zustand for game state + WS updates

- Lobby: create table with optional password, share join code, waiting room

- Game board: dice roll animation, card activation highlights, coin flow

- Responsive layout (desktop + mobile)

# Phase 5 — Multiplayer, AI & Polish

WEEK 19–22

5.1  Online Multiplayer

- WebSocket-based real-time sync across all players

- Reconnect handling (player drops and rejoins)

- Turn timer (optional: kick idle players)

5.2  AI Opponent

- Basic AI: greedy strategy (always buy most expensive available card)

- Intermediate AI: prioritizes card combos and landmark building order

- AI fills empty seats so games can start with fewer human players

5.3  Polish

- Sound effects: dice roll, coin clink, card purchase, win fanfare

- Animations: card activation sequence, turn transitions

- Mobile optimization

- Accessibility: keyboard nav, color-blind friendly card icons

# Phase 6 — Launch

WEEK 23–24+

- Deploy frontend to Vercel, backend to Railway or Render

- Set up PostgreSQL (managed, e.g. Supabase or Railway Postgres)

- Beta testing with a small group of real players

- Fix launch-blocking bugs

- Monitor performance and WebSocket stability

- Post-launch: collect feedback and plan expansion (e.g. more card sets, tournaments)

# Milestone Summary

| Phase | Milestone | Target | Status |
| --- | --- | --- | --- |
| Phase 1 | Rules & design docs complete | Week 2 | — |
| Phase 2 | WordPress MVP: lobby + auth + core game loop | Week 8 | — |
| Phase 3 | Review, bug-fix & migration plan | Week 9–10 | — |
| Phase 4 | React/Python: single + local play working | Week 16 | — |
| Phase 5 | Online multiplayer + AI opponent live | Week 22 | — |
| Phase 6 | Public launch | Week 24+ | — |

# MVP Scope Definition

In Scope for MVP (Phase 2)

- Table creation with join code + optional password

- Email registration + guest play

- Online multiplayer for 2–5 players via AJAX polling

- Full Machi Koro Plus card set and rules

- Score saving for registered users

- Basic leaderboard

Out of Scope for MVP

- WebSocket real-time sync (upgrade in Phase 4)

- AI opponent

- Mobile-optimized UI

- Sound & animation

- Additional card expansions